## Untitled
Asset ID | Asset Name | Threat | Vulnerability | Inherent Risk Score | Treatment Decision | Proposed Control & ISO 27001:2022 Annex A Mapping | Residual Risk Score
AST-01 | Production Kubernetes Cluster (AWS EKS) | Unauthorized container escape or cluster takeover | Misconfigured RBAC permissions or unpatched container runtime vulnerabilities | 20 | Mitigate | Enforce strict least-privilege RBAC, automated container vulnerability scanning in pipelines, and network segmentation policies. (Annex A.8.9 / A.8.20) | 4
AST-02 | Multi-Tenant Customer Database (PostgreSQL) | SQL injection or unauthorized cross-tenant data access | Weak database encryption, exposed public endpoints, or missing input validation | 25 | Mitigate | Implement encryption at rest/in transit, private VPC subnet isolation, parameterized queries, and strict database security groups. (Annex A.8.24 / A.8.12) | 5
AST-03 | GitHub Enterprise Code Repositories (IP) | Malicious insider or credential theft exposing source code | Lack of branch protection rules, code secrets scanning, or hardware MFA on developer accounts | 16 | Mitigate | Enforce mandatory hardware-backed FIDO2 MFA, automated secrets scanning in git hooks, and strict code review pull-request policies. (Annex A.8.31 / A.9.4) | 4
AST-04 | Cloud Admin Access & AWS IAM Master Keys | Account takeover and full cloud infrastructure compromise | Long-lived static access keys and lack of multi-person authorization for critical actions | 20 | Mitigate | Mandate AWS IAM Identity Center with temporary SSO sessions, disable root user access keys, and enforce hardware tokens. (Annex A.9.2 / A.9.4) | 4
AST-05 | Corporate Identity Provider (Okta / Google Workspace) | Phishing, credential stuffing, and corporate takeover | Employees using weak passwords or lacking phishing-resistant multi-factor authentication | 15 | Mitigate | Enforce enterprise-wide WebAuthn/YubiKey hardware tokens, automated device posture checks, and session time limits. (Annex A.5.17 / A.9.4) | 3
AST-06 | Employee Workstations / Laptops | Phishing & Malware Execution | Lack of regular security awareness training or multi-factor authentication for corporate apps | 15 | Mitigate | Enforce mandatory security awareness training, phishing simulation tests, and hardware-backed MFA. (Annex A.6.3 / A.9.4) | 3
AST-07 | CI/CD Deployment Pipeline (GitHub Actions) | Supply Chain Code Injection | Using unvetted third-party open-source libraries and scripts without security scanning | 20 | Mitigate | Integrate automated Software Composition Analysis (SCA) and secure code reviews into the pipeline. (Annex A.8.8 / A.8.31) | 4
AST-08 | Encrypted Customer Backups (AWS S3) | Ransomware Deletion or Data Corruption | Backups stored in the same administrative account without write-once-read-many (WORM) protections | 20 | Mitigate | Enable AWS S3 Object Lock (WORM state), cross-region replication, and strict multi-person authorization for deletion. (Annex A.8.13 / A.8.24) | 4
AST-09 | Internal HR & Employee Database | Unauthorized Internal Data Harvesting | Overly permissive default role-based access control (RBAC) allowing all staff to view records | 15 | Mitigate | Implement strict Principle of Least Privilege (PoLP) and quarterly manual access reviews. (Annex A.9.1 / A.9.2) | 3
AST-10 | Office Wi-Fi & Network Infrastructure | Rogue Device / Man-in-the-Middle Attack | Open corporate Wi-Fi network or weak pre-shared keys for office visitors and staff | 12 | Mitigate | Deploy WPA3-Enterprise 802.1X authentication, guest network segmentation, and certificate-based device profiling. (Annex A.7.4 / A.8.21) | 3
AST-11 | Third-Party Vendor API Integrations | Third-Party Data Breach / Supply Chain Compromise | Unvetted vendor security posture, overly broad OAuth scopes, and lack of API rate-limiting | 16 | Mitigate | Conduct rigorous vendor security assessments, enforce least-privilege OAuth scopes, and monitor API traffic anomalies. (Annex A.5.19 / A.8.28) | 4
AST-12 | SIEM & Log Management Infrastructure (Wazuh / Splunk) | Log Tampering or Blind Spots in Monitoring | Unencrypted log transmission, lack of log retention policies, or missing agents on core servers | 15 | Mitigate | Centralize log aggregation, enable immutable write-once log storage, and enforce automated alerting for critical security events. (Annex A.8.15 / A.8.16) | 3
AST-13 | Customer Support Ticketing System (Zendesk / Jira) | Social Engineering / Unauthorized PII Access by Support Agents | Lack of ticket data masking, excessive agent permissions, or weak session controls | 12 | Mitigate | Mask sensitive customer data fields, enforce role-based ticket access, and audit agent activity logs. (Annex A.8.11 / A.9.4) | 3
AST-14 | Public-Facing Corporate Website & Marketing CMS | Website Defacement or Malicious Redirection | Outdated CMS plugins, unpatched vulnerabilities, or weak administrator passwords | 12 | Mitigate | Implement automated plugin vulnerability scanning, Web Application Firewall (WAF), and isolated hosting architecture. (Annex A.8.8 / A.8.26) | 3
AST-15 | Disaster Recovery & Business Continuity Plan (DRP/BCP) | Extended Service Outage due to Ransomware or Cloud Region Failure | Untested backup restoration procedures and lack of documented failover runbooks | 20 | Mitigate | Conduct annual full-scale disaster recovery drills, establish multi-region redundancy, and maintain documented BCP runbooks. (Annex A.5.29 / A.5.30) | 4